## Sheet1
Task | Optimistic estimate | Most likely estimate | Pessimistic estimate | Final estimate
Business Understanding |  |  |  | 11 days
Objectives |  |  |  | 9 days
Resource Allocation | 1 | 2 | 3 | 3 days
Project Planning | 2 | 3 | 4 | 3 days
Scope Definition | 2 | 3 | 4 | 3 days
Key Stakeholders | 1 | 2 | 3 | 2 days
Define Success Criteria |  |  |  | 3 days
Align success criteria | 1 | 2 | 3 | 2 days
KPI's | 2 | 3 | 4 | 3 days
Data Understanding |  |  |  | 10 days
Explore Relevant Datasets |  |  |  | 3 days
Historical, transaction, energy consumption | 1 | 2 | 3 | 2 days
Identifying datasets | 1 | 2 | 3 | 2 days
Acquire the dataset | 1 | 2 | 3 | 2 days
Explore the dataset | 1 | 2 | 3 | 2 days
Checking for assess keys | 1 | 2 | 3 | 2 days
Data Quality, Characteristics and Feature |  |  |  | 7 days
Real-Time Weather data |  |  |  | 3 days
API's | 2 | 3 | 4 | 3 days
Environment agencies, research organizations | 2 | 3 | 4 | 3 days
Filtering the time-line | 2 | 3 | 4 | 3 days
Data Preparation |  |  |  | 11 days
Cleaning of Data &amp; Handle categorical variable |  |  |  | 5 days
Missing values | 2 | 3 | 4 | 3 days
Outliners | 2 | 3 | 4 | 3 days
Inconsistencies | 2 | 3 | 4 | 3 days
Standardized units and formats | 2 | 3 | 4 | 3 days
Handle categorical variables | 2 | 3 | 4 | 3 days
Feature Engineering |  |  |  | 3 days
Time-based features | 2 | 3 | 4 | 3 days
Lagged variable for historical patterns | 2 | 3 | 4 | 3 days
Derived features | 2 | 3 | 4 | 3 days
Preprocessing and Granularity of data |  |  |  | 3 days
Temporal Granularity | 2 | 3 | 4 | 3 days
Data Aggregation | 2 | 3 | 4 | 3 days
Spatial Granularity | 2 | 3 | 4 | 3 days
Split data |  |  |  | 3 days
Train-Validation-Test Split | 2 | 3 | 4 | 3 days
Time-based splitting for temporal data | 2 | 3 | 4 | 3 days
Balanced representation of classes in each split | 2 | 3 | 4 | 3 days
Modeling |  |  |  | 12 days
Model 1 |  |  |  | 9 days
Model Training and Tuning | 2 | 3 | 4 | 3 days
Model Evaluation | 2 | 3 | 4 | 3 days
Hyper-parameter tuning | 2 | 3 | 4 | 3 days
Model 2 |  |  |  | 9 days
Model Training and Tuning | 2 | 3 | 4 | 3 days
Model Evaluation | 2 | 3 | 4 | 3 days
Hyper-parameter tuning | 2 | 3 | 4 | 3 days
Model 3 |  |  |  | 9 days
Model Training and Tuning | 2 | 3 | 4 | 3 days
Model Evaluation | 2 | 3 | 4 | 3 days
Hyper-parameter tuning | 2 | 3 | 4 | 3 days
Model 4 |  |  |  | 9 days
Model Training and Tuning | 2 | 3 | 4 | 3 days
Model Evaluation | 2 | 3 | 4 | 3 days
Hyper-parameter tuning | 2 | 3 | 4 | 3 days
Implement cross-validation to assess model generalization |  |  |  | 3 days
Fine-tune hyperparameters | 2 | 3 | 4 | 3 days
Optimization techniques | 2 | 3 | 4 | 3 days
Remove complexity and cost | 2 | 3 | 4 | 3 days
Learning rate in optimization algorithms | 2 | 3 | 4 | 3 days
Evaluation |  |  |  | 3 days
Assess Model Performance | 2 | 3 | 4 | 3 days
Sensitivity Analysis | 2 | 3 | 4 | 3 days
Deployment |  |  |  | 11 days
Implement Project Deployment | 2 | 3 | 4 | 3 days
Risk management | 2 | 3 | 4 | 3 days
Monitoring tools for model performance | 2 | 3 | 4 | 3 days
Maintenance plan for periodic updates | 2 | 3 | 4 | 3 days
Project Pipeline | 4 | 6 | 8 | 6 days
Database | 2 | 3 | 4 | 3 days
Cloud (GCP/AWS) | 2 | 3 | 4 | 3 days
Python | 2 | 3 | 4 | 3 days
Analytics |  |  |  | 5 days
Visualization | 2 | 3 | 4 | 3 days
Python | 2 | 3 | 4 | 3 days
Power BI | 2 | 3 | 4 | 3 days
Dashboards | 2 | 3 | 4 | 3 days
Word cloud | 2 | 3 | 4 | 3 days
Power BI | 2 | 3 | 4 | 3 days
Insights | 1 | 2 | 3 | 2 days
Reports | 1 | 2 | 3 | 2 days